## Indicators
Code | Indicator | Baseline | Target | This period | Life of project to date | % of target | Unit | Status
WS-IMP1 | Percentage of households reporting diarrhoea in a child under five in the last two weeks | 31 | 18 | 21 | 21 | 117% | % | VERIFIED
WS-OC1a | Percentage of households using an improved drinking water source | 42 | 75 | 72 | 72 | 96% | % | VERIFIED
WS-OC1b | Percentage of households with access to a functional, unshared latrine | 28 | 55 | 52 | 52 | 95% | % | VERIFIED
WS-OC1c | Percentage of water points with free chlorine residual of at least 0.2 mg/l | 40 | 90 | 88 | 88 | 98% | % | VERIFIED
WS-OC2a | Percentage of households with a handwashing facility with soap and water | 22 | 60 | 63 | 63 | 105% | % | VERIFIED
WS-OC2b | Percentage of water point committees that are functional | 15 | 80 | 78 | 78 | 98% | % | VERIFIED
WS-OP1.1 | Number of water points constructed or rehabilitated | 0 | 20 | 3 | 16 | 80% | water points | VERIFIED
WS-OP1.1b | Number of people with new or improved access to safe water | 0 | 30000 | 6900 | 26000 | 87% | people | VERIFIED
WS-OP1.2 | Number of household latrines constructed | 0 | 600 | 70 | 585 | 98% | latrines | VERIFIED
WS-OP1.3 | Number of school and health-facility WASH blocks constructed | 0 | 8 | 2 | 8 | 100% | blocks | VERIFIED
WS-OP2.1 | Number of people reached with hygiene promotion | 0 | 24000 | 3000 | 22900 | 95% | people | VERIFIED
WS-OP2.2 | Number of water point committees established and trained | 0 | 16 | 1 | 15 | 94% | committees | VERIFIED
WS-OP2.3 | Number of water quality tests conducted | 0 | 320 | 50 | 340 | 106% | tests | VERIFIED
WS-OP2.4 | Number of households receiving hygiene kits and household water treatment | 0 | 2500 | 900 | 2600 | 104% | households | VERIFIED

## Activities
Title | Date | Location | Participants