## Indicators
Code | Indicator | Baseline | Target | Achievement | Unit | Status
O1 | Number of people with access to safe drinking water | 0 | 14000 | 2800 | people | VERIFIED
O2 | Percentage of surveyed households with a handwashing station with soap | 28 | 75 | 76 | % | VERIFIED
1.1 | Number of water points rehabilitated and functional | 0 | 24 | 4 | water points | VERIFIED
1.2 | Number of water user committees formed and trained | 0 | 12 | 2 | committees | VERIFIED
1.3 | Percentage of tested water samples meeting residual chlorine standard (0.2-0.5 mg/L) | 55 | 90 | 91 | % | VERIFIED
2.1 | Number of household latrines constructed and in use | 0 | 300 | 55 | latrines | VERIFIED
2.2 | Number of schools with gender-separated WASH blocks completed | 0 | 6 | 1 | schools | VERIFIED
2.3 | Number of people reached with hygiene promotion | 0 | 12000 | 2000 | people | VERIFIED

## Activities
Title | Date | Location | Participants
A1.1 — Rehabilitation of 4 water point(s), Dadu (Kachho) | 2026-08-06T00:00:00.000Z | Dadu (Kachho), Dadu district | 2800
A1.2 — Water user committee formation and training, Johi | 2026-08-12T00:00:00.000Z | Johi, Dadu district | 24
A1.3 — Chlorination and water quality testing, Mehar | 2026-08-18T00:00:00.000Z | Mehar, Dadu district | 0
A2.1 — Household latrine construction, Mehar | 2026-08-22T00:00:00.000Z | Mehar, Dadu district | 55
A2.2 — School WASH block construction, Khairpur Nathan Shah | 2026-08-25T00:00:00.000Z | Khairpur Nathan Shah primary school, Dadu district | 0
A2.3 — Hygiene promotion sessions and handwashing demonstrations, Dadu | 2026-08-28T00:00:00.000Z | Dadu, Dadu district | 2000